Absolutely—this is a common gap in standard product help: it tells you what each piece does, but not how to design the whole system so team templates, lifecycle templates, groups, users, and teams all work together for a real business.

Below is a practical implementation plan you can follow for a typical industrial manufacturer that builds configurable and serviceable 3D printers. It’s organized as a step-by-step playbook with workshops, design decisions, example configurations, and deliverables at each stage.

## 0) Guiding Principles

- Context-driven security: Most access is governed by Context Teams + ACLs—not ad hoc per-user grants.

- Template-first: All repeatable behavior should be driven by Team Templates and Lifecycle Templates (LCs), not manual role assignment.

- Role-based mapping: Define business roles → Windchill roles → access policies. Avoid user-specific logic.

- Separation of concerns:

  - Lifecycle controls state & process gates (e.g., WIP → In Review → Released → Obsolete).

  - Teams control who can do what at those gates.

  - Policies control how permissions apply to objects at each state.

- One source of truth:

  - Engineering BOM (E-BOM) in WTParts with CAD associations.

  - Service BOM (S-BOM) derived/redlined for serviceability.

  - Option & Variant logic established at product line level.

## 1) Scope & Reference Model (2–3 Workshops)

### 1.1 Business Scope

- Products: Industrial 3D printer family; variants differ by:

  - Build volume (Small, Medium, Large)

  - Extruder configurations (single/dual)

  - Materials (PLA, ABS, CFR Nylon)

  - Control systems (Standard vs. Industrial PLC)

  - Service offerings (Basic, Gold, Platinum)

- Processes to cover:

  - CAD → WTPart association, E-BOM management

  - Change Management (ECR/ECO), Promotion-only flows for low-risk items

  - Release and baselines for configurable models

  - Service BOM, service parts, and documentation (work instructions, IPL)

  - Supplier collaboration (RFQ/AML/AVL optional phase 2)

### 1.2 Governance Deliverables

- Operating Model: RACI + role catalog

- Context Strategy: One Product Context per product line (e.g., “Printers”), separate Service Context (optional)

- Library Strategy: Common library for shared standards/parts

- Naming/Numbering: Autonumbering patterns for WTPart, EPMDoc, WTDoc, Change objects

## 2) Role & Access Model (Workshops + Draft)

### 2.1 Business Role Catalog → Windchill Roles

Map business roles to Windchill OOTB roles (or custom) used in Context Teams:

| Business Role | Windchill Role (Context Team) | Notes |
| --- | --- | --- |
| Product Manager | Product Manager | Owns baselines, releases, variant structure |
| Lead Mechanical Engineer | Design Engineer | Creates/owns EPMDoc/WTPart, propose releases |
| Manufacturing Engineer | Manufacturing | Contributes MBOM/plans |
| Service Engineer | Service | Builds S-BOM/redlines service parts |
| Quality Engineer | Quality | Reviews at Release gates |
| Configuration Manager | Configuration Manager | Variant rules/option sets; approval |
| Doc Control | Document Manager | Controls WTDocuments, publishing |
| Change Admin | Change Administrator I/II | Routes changes; approves ECO |
| Supplier (ext.) | Supplier (shared team only) | Limited access via Shared Team/Project |

Keep roles minimal. Resist creating many near-duplicate roles—complexity multiplies in ACLs.

### 2.2 Access Policy Backbone (High-Level)

- Pre-Release states (In Work, Under Review):

  - Design Engineers: Read/Download/Modify on their own WIP objects.

  - Team reviewers (Quality/Manufacturing/Service): Read during review; annotate, not modify.

- Released:

  - Everyone in Product Context: Read/Download Released items.

  - Doc Control/CM: Modify for supersedure only through Change process.

- Obsolete:

  - Hidden from non-admin search; still readable by CM/Doc Control.

Actual policy implementation will be in Policy Administration + Lifecycle State Permissions.

## 3) Object Strategy & Templates

### 3.1 Object Types & Subtypes (where needed)

- WTPart: E-BOM master, with subtypes:

  - WTPart/Make, WTPart/Buy, WTPart/ConfigurableModule (assemblies with options)

- EPMDocument/CAD: Creo files, associated to WTParts via Owner/Content links.

- WTDocument: Specs, Work Instructions, Service Manuals

- Change Objects: ECR, ECO (Promotion Request for trivial updates)

- Service Objects (if using Service Structure): WTPart/Service or S-BOM view

### 3.2 Lifecycle Templates (per object class)

WTPart_LC (Engineering parts):

- States: In Work → Design Review → Released → Obsolete

- Transitions:

  - In Work → Design Review: requires Peer Review task

  - Design Review → Released: via ECO (preferred) or Promotion (low-risk, doc-only)

  - Released → Obsolete: ECO only

- Workflow Roles used: Author, Reviewer, Approver, Change Admin, Doc Control

EPMDoc_LC (CAD):

- Typically mirrors parts but allows WIP iterations more freely; release must align with WTPart.

WTDocument_LC (Docs):

- In Work → Doc Review → Released → Superseded

- Promotion allowed for minor updates with Doc Control approval.

Change_LC:

- ECR: triage → analysis → decision (Approve/Reject) → if approved, auto-create ECO

- ECO: implementation plan → tasks (CAD update, Part update, Document update) → verification → close

### 3.3 Team Templates (Context & Shared Team)

Context Team Template: Product – Printers

- Members by Role:

  - Product Manager: Named users or group GRP_ProductManagers

  - Design Engineer: GRP_Design_Mech, GRP_Design_EE

  - Configuration Manager: GRP_ConfigMgmt

  - Quality: GRP_Quality

  - Manufacturing: GRP_MfgEng

  - Service: GRP_ServiceEng

  - Document Manager: GRP_DocControl

  - Change Administrator II: GRP_ChangeAdmin

- Usage: Applied automatically to the Printers Product Context.

Shared Team Template: “Printers – Supplier Collaboration”

- Roles: Supplier, Supplier QA

- Mapped groups: GRP_Suppliers_<Domain>

- Usage: Referenced in workflows (ECO/ECR tasks to Supplier), or Projects when collaborating.

Rule: Use Context Team for internal standing access. Use Shared Team when specific external parties or cross-context participants need scoped access.

## 4) Option & Variant Planning (for Configurable 3D Printers)

### 4.1 Option Model

- Option Sets (at Product Context “Printers”):

  - Build Volume: S / M / L

  - Extruder Configuration: Single / Dual

  - Material Capability: PLA / ABS / CFR

  - Controller: Standard / Industrial PLC

  - Service Package: Basic / Gold / Platinum

- Rules:

  - If Extruder=Dual → require Material Capability != CFR (example constraint)

  - If Controller=Industrial PLC → require Service Package ∈ {Gold, Platinum}

### 4.2 Configurable Modules

- Example WTPart/ConfigurableModule: “Printhead Assembly”

  - Variant conditions determined by Extruder Configuration and Material Capability

- Use Aliases (synonyms) for options only if UX requires; maintain canonical internal option keys.

### 4.3 Lifecycle & Team Interactions

- Configuration Manager owns Option Set governance (LC state changes for OptionSets often require CM approval).

- Released variant specs are baselineable with product configurations.

## 5) Lifecycle ↔ Team ↔ Policy Alignment

Pattern: For each Lifecycle State, specify which Team Roles have what permissions. Then implement in Policy Administration under the object type + state.

Example: WTPart (Engineering Parts)

| LC State | Team Role | Permissions |
| --- | --- | --- |
| In Work | Design Engineer | Read, Download, Modify, Change Domain |
| In Work | Quality / Mfg / Service | Read, Download |
| Design Review | Reviewer (Team placeholder) | Read, Download, Annotate |
| Released | All Context Members | Read, Download |
| Released | Doc Control / CM | Revise via Change (not direct Modify) |
| Obsolete | CM / Doc Control | Read (limited), No Modify except via ECO |

Implement reviewers by workflow assignments to a Reviewers role placeholder bound to Team roles.

## 6) Change Governance

### 6.1 When to use Promotion vs. ECR/ECO

- Promotion Request: Minor doc updates (spelling, format), metadata-only changes with no BOM impact.

- ECR/ECO: Any functional change, form/fit/function, BOM structure, CAD geometry, or safety/regulatory impact.

### 6.2 Templates

- ECR Template:

  - Activities: Submit → Triage (Change Admin) → Impact Analysis (Design, Mfg, Service, Quality) → CAB decision

- ECO Template:

  - Activities: Plan → Implement (tasks for CAD, Parts, Docs) → Verify → Release → Close

- Role gating: Approvals require Change Admin + Quality + Product Manager.

## 7) Directory, Groups, and Provisioning

### 7.1 Identity Sources

- Integrate with corporate identity (AD/AAD/LDAP).

- Windchill Groups (prefix with GRP_), each maps to a business function.

- Avoid putting users directly in Context Teams; use groups.

### 7.2 Provisioning Workflow

- HR/IT adds user to corporate group (e.g., “Design Engineering”).

- Automated sync adds user to GRP_Design_Mech.

- Context Team Template already includes GRP_Design_Mech → user gains contextual access.

## 8) Implementation Phases & Deliverables

### Phase A: Foundation (2–4 weeks)

- Decisions:

  - Contexts (Product: Printers, Library: Common, optional Service context)

  - Numbering & Naming schemes

  - Role Catalog & Groups

- Build:

  - Create Groups in Windchill

  - Create Context Team Template and assign groups

  - Baseline Policy Administration defaults (start OOTB, then tighten)

- Deliverables:

  - Role Matrix (RACI)

  - Context & Team Template definitions

  - Policy matrix per Object Type & State

### Phase B: Lifecycles & Workflows (3–6 weeks)

- Design:

  - Lifecycle templates (WTPart, EPMDoc, WTDoc, Change)

  - Workflows for Review, Promotion, ECR, ECO

- Build:

  - Implement LC templates & routing

  - Map workflow roles to Team roles

  - Notification & task SLAs

- Deliverables:

  - LC BPMN diagrams (or screenshots)

  - Workflow definitions + test plans

  - Approval matrices

### Phase C: Options & Variants (3–5 weeks)

- Design:

  - Option Sets, constraints, and Configurable Modules

- Build:

  - Create Option Sets in Product context

  - Assign rules to modules

- Deliverables:

  - Option catalog & rulebook

  - Example configured BOMs

  - Variant release/baseline procedure

### Phase D: Service Structures (2–4 weeks)

- Design:

  - S-BOM derivation rules (1:1 vs. simplified serviceable units)

  - Redline process, service part identification, supersedure rules

- Build:

  - Service BOM view or dedicated Service context

  - Lifecycle for service docs (manuals, WIs)

- Deliverables:

  - S-BOM governance guide

  - Service doc LC & templates

  - Publication pipeline (PDF, HTML, translations if any)

### Phase E: Hardening & Rollout (2–4 weeks)

- Hardening:

  - Security tests, search/visibility checks

  - Performance review on large assemblies

- Training:

  - Role-based guides: Designer, Reviewer, CM, Doc Control, Service

- Migration (if needed):

  - CAD/Part alignment (Owner vs. Content links)

  - Data cleansing rules for states/ownership/attributes

- Deliverables:

  - UAT sign-off

  - Admin runbook

  - Training assets & quick cards

## 9) Example Configuration (Concrete, Ready-to-Use)

### 9.1 Team Template: “Printers – Product Context”

1 Team Roles: 2 - Product Manager -> GRP_ProductManagers 3 - Design Engineer -> GRP_Design_Mech, GRP_Design_EE 4 - Configuration Manager-> GRP_ConfigMgmt 5 - Quality -> GRP_Quality 6 - Manufacturing -> GRP_MfgEng 7 - Service -> GRP_ServiceEng 8 - Document Manager -> GRP_DocControl 9 - Change Admin II -> GRP_ChangeAdmin 10 Shared Team (optional): 11 - Supplier -> GRP_Suppliers_EMEA, GRP_Suppliers_AMER

### 9.2 Lifecycle: “WTPart – Printers Engineering”

1 States: In Work -> Design Review -> Released -> Obsolete 2 Key Gates: 3 - In Work -> Design Review: Task "Peer Design Review" (Reviewers from Quality + Peer Designer) 4 - Design Review -> Released: via ECO OR Promotion tiered rule 5 - Released -> Obsolete: ECO only; doc control verifies supersedure

### 9.3 Policy Snippet (illustrative)

- WTPart / In Work:

  - Design Engineer: Read, Download, Modify, Change Domain

  - Others: Read (if on Team), no Modify

- WTPart / Released:

  - All Context Members: Read, Download

  - Doc Control / CM: Revise via Change, not direct Modify

- WTDocument / Released:

  - Document Manager: Can supersede via Promotion (minor) or ECO (major)

  - General: Read

### 9.4 Change Templates

- ECR:

  - Participants: Requestor (any), Change Admin, Quality, Design, Mfg, Service

  - Outcome: Approve → auto-create ECO; Reject → Close

- ECO:

  - Tasks: CAD update (EPMDoc), Part update (WTPart), Doc update (WTDoc), Verification

  - Final Approval: Change Admin + Quality + Product Manager

## 10) Quality Checks & Guardrails

Use this as a punch list during build and UAT:

- Team Template coverage: Every Product Context uses the Context Team Template; no direct user additions (except emergencies).

- Workflow role bindings: Every workflow swimlane role maps to a Team role (no hard-coded users).

- Released visibility: Search as a non-team member—verify Released items are discoverable if intended.

- State transitions: Attempt invalid transitions (e.g., Released → In Work) to confirm blocks work.

- Promotion vs ECO enforcement: Try to promote a part with BOM changes → should be blocked; require ECO.

- CAD–WTPart alignment: Confirm Owner link is correct; publishing/release handshake works.

- Option Sets: Configure illegal combination—ensure rule prevents or warnings are clear.

- Service derivation: E-BOM → S-BOM propagation works; redlines tracked; service docs synced.

- Audit logging: Key approvals, sign-offs, and state changes are traceable.

- Performance: Open a Large variant assembly; verify load times and filtering options (variant expression) are acceptable.

## 11) Training & Adoption

- Role-based quick guides:

  - Designers: Check-in, Associate to WTPart, WIP best practices, request review/promotion.

  - Reviewers: Where to find tasks, how to annotate/approve.

  - Change Admins: ECR triage, ECO planning, baselines, effectivity.

  - Service: Create S-BOM, identify service parts, publish service docs.

- Visual Aids:

  - “Who can do what at each state” poster.

  - “Change decision tree: Promotion vs ECR/ECO.”

  - “Option & Variant rulebook” cheat sheet.

## 12) What I Can Build Next for You

If you’d like, I can produce:

- A matrix workbook (Excel) with:

  - Roles × Lifecycle States × Permissions

  - Team Template → Group mappings

  - Object type → Lifecycle Template mapping

- Workflow diagrams (review, promotion, ECR, ECO) ready for slides.

- A RACI for change process and release.

- A starter Policy Admin export (documented, not system export) describing exact ACL entries per state.

### Quick Follow-up Questions to Tailor This Plan

- Do you want a single Product Context (“Printers”) or one per Product Family (e.g., “F-Series”, “L-Series”)?

- Should Service live in the same Product Context or a separate Service Context with its own Team Template?

- Which external collaboration scenario is in scope first—suppliers or field service partners?

- Do you want me to generate the Excel role/LC/policy matrix now so your team can execute directly?

If you share your current org roles and any must-keep rules you already use, I’ll plug them into the templates above and deliver ready-to-use matrices and diagrams.